## Slide 1: Problem Statement | Pain Points | Goal

### 🔍

### Problem Statement

The Partner Onboarding and Document Enablement process for ECM Repository Services currently involves 27 stages, multiple stakeholder hand-offs, and several dependency systems (APG, Kafka, Retention, Security, Metadata, Profiles, etc.).

Despite having a well-defined workflow, it remains highly manual, resulting in delays, inconsistencies, and lack of visibility across the lifecycle — from intake creation to production deployment.

### ⚠️

### Critical Pain Points

- Turnaround Time: The current onboarding and document migration journey often takes 6–9 months, and in some cases, exceeds a year before documents move from test repositories to production.

- Manual Coordination: Partner Onboarding Resources spend large portions of time following up with multiple dependent teams for metadata, retention, Kafka, and APG approvals.

- Fragmented Data: Key inputs like Intake forms, RM Questionnaires, Transition Pages, and Volumes are stored across Excel files, Confluence pages, and emails — creating information silos.

- Limited Automation: No end-to-end automation exists for orchestration, validation, or readiness checks; the process relies on human tracking and follow-ups.

- Low Predictability: There is no early risk identification or predictive mechanism to flag delayed dependencies.

- Complex Approval Chain: Service account creation, Kafka provisioning, and metadata validation all depend on multiple approvers, often across time zones.

- Testing Delays: Late UAT or load-testing sign-offs cause missed release windows.

- Repository Migration Challenges: When partners already have documents on repositories like Amazon S3, shared drives, or other legacy content stores, the process to onboard, validate, and move them to ICMP production takes months, adding to operational costs and compliance delays.

### 🎯

### Goal / Hackathon Agenda

The objective is to design a True Agentic AI solution powered by Model Context Protocol (MCP) and Agentic Orchestration Framework that can:

- Observe, reason, and act autonomously to manage dependencies, tasks, and stakeholder updates.

- Enable self-learning workflow orchestration for intake to production deployment.

- Use MCP-based context synchronization to allow different agents to exchange context — e.g., between metadata validation, retention setup, and API readiness.

- Provide an AI-powered command center dashboard that can track partner progress, dependencies, and readiness with real-time SLA predictions.

- Significantly reduce turnaround time for partner onboarding and document migration from 6–9 months to 2–4 weeks (1–2 sprints) through smart automation, pre-validation, and dynamic risk prediction.

- Support direct document migration from external repositories (e.g., Amazon S3, Shared Drives) into ICMP while preserving metadata, retention rules, and audit trail — ensuring compliance and zero manual steps.

- Auto-generate release transition pages, approvals, and change requests using intelligent context chaining.

### 💡

### Expected Outcome

- A single unified AI platform — Onboard360 AI — that redefines the partner onboarding and document migration journey using Agentic Intelligence and MCP interoperability.

- Enables “self-orchestrating onboarding”, where intelligent agents manage the flow across all stages without human micromanagement.

- Delivers real-time insights, auto-generated documentation, and predictive delay detection for proactive resolution.

- Transforms the onboarding experience into a 2–4 week agile sprint model, with measurable gains in efficiency, compliance, and partner satisfaction.

## Slide 2: Journey Overview | Activities | Bottlenecks | Timelines

| Stage Group | Core Activities | Bottlenecks / Challenges | Planned Duration | Current Average Duration |
| --- | --- | --- | --- | --- |
| 1. Intake & Triage | Intake creation, DoR validation, triage scheduling | Missing details, lengthy triage loops | 1–2 weeks | 4–6 weeks |
| 2. Prioritization | LOB ranking, BigRoom planning | Capacity constraints, dependency conflicts | 1 week | 2–3 weeks |
| 3. Scope & Planning | Scope validation, story/task definition | Ambiguous requirements | 2 weeks | 4 weeks |
| 4. API / Gateway Setup | App ID, certificates, service accounts | Approval delays, manual requests | 1 week | 3 weeks |
| 5. Notifications / Kafka | Consumer group creation, topic validation | KWES queue delays, cert dependencies | 1–2 weeks | 4 weeks |
| 6. Document Classification | Sample sharing, doc classification, AI split | Imaging governance backlog | 1 week | 3 weeks |
| 7. Partner Agreements & Volume | System agreement, volume collection, SPLI | Partner inputs missing | 1 week | 3 weeks |
| 8. Metadata & Security | Metadata mapping, relationship keys, LOB setup | Multi-LOB coordination, unclear ownership | 2 weeks | 5 weeks |
| 9. Retention & Profiles | RM questionnaire, retention logic, profiles | Record coordinator approvals, config load | 2 weeks | 6 weeks |
| 10. Testing & Validation | Unit, Integration, UAT, Load testing | Environment readiness, sign-off delays | 3 weeks | 6–8 weeks |
| 11. Release & Change Mgmt | Transition page, CRs, APG approvals | Late approvals, incomplete data | 1 week | 3 weeks |
| 12. Production Validation | Tech + business validation, sign-offs | Partner business validation delays | 1 week | 3–4 weeks |

### ⏳

### Cycle Summary

- Planned Total: ~16–18 weeks

- Actual Average: ~30–36 weeks (6–9 months in complex cases)

- Target with Agentic AI + MCP: 2–4 weeks (1–2 sprints)

### 🚀

### Challenge to Participants

“Design an AI-driven, true agentic solution using Model Context Protocol (MCP) that can autonomously manage partner onboarding, dependencies, and document migration from any source (e.g., Amazon S3, shared drives) into ICMP — cutting turnaround time from 6–9 months to under 4 weeks.”

## 🟩

## SLIDE 1 – Problem Statement | Pain Points | Hackathon Goal

### 🔍 Problem Statement

The current Partner Onboarding process for ECM Repository Services spans 27 manual stages —from Intake to Production Validation— and involves dozens of hand-offs across LOBs, Product Owners, SMEs, Platform Support and Governance teams.

Despite defined procedures, the journey suffers from high turnaround time, dependency chain delays, and limited visibility of where each partner is in the process.

### ⚠️ Critical Pain Points

- Excessive Manual Steps (27 stages): Excel-based intake, email threads, manual JIRA linkages cause redundant data entry and human errors.

- Low Visibility: No single dashboard showing partner progress or pending actions across LOBs.

- Follow-Up Fatigue: Hundreds of reminders and status emails sent each week by Partner Onboarding Resources (SMEs).

- Dependency Bottlenecks: Security, Retention, Kafka, and API Gateway approvals move sequentially instead of in parallel.

- Documentation Fragmentation: Critical artifacts (Intake, RM Questionnaire, Transition Pages) stored in multiple locations.

- Release Readiness Gaps: Delays in UAT sign-off and Change Request approvals lead to missed release windows.

- Resource Overload: Each Onboarding Resource handles 15-20 partners in parallel with manual tracking.

- No AI-Driven Insights: Lack of predictive analytics for risk, ETA, or stage delays.

### 🧠 Hackathon Goal / Agenda

Theme: “Agentic Automation for Partner Onboarding Journey – Onboard360 AI”

Design AI-driven agents that can observe, decide and act to streamline each stage.

Hackathon Tracks

- AI Copilot for Partner Onboarding: Conversational agent to create Intakes, guide DoR readiness, auto-populate JIRA.

- Journey Orchestrator: Agent to track partner progress, auto-trigger alerts, generate transition pages, and handle approvals.

- Smart Validator: Automate metadata, profile, and security checks through model-context AI agents.

- Predictive Planner: Use historical timelines to forecast delays and recommend next actions.

- Data Integrator: Unified view of JIRA + Confluence + SharePoint for live progress tracking.

Outcome: Prototypes that reduce overall onboarding time by > 60 %, and automate > 70 % of repetitive manual steps.

## 🟦

## SLIDE 2 – Partner Onboarding Journey Overview | Activities | Bottlenecks | Timelines

| Stage Group | Representative Stages | Core Activities | Typical Bottlenecks | Avg Planned Duration | Typical Actual Duration |
| --- | --- | --- | --- | --- | --- |
| 1 – Intake & Triage | Stage 1: Intake → Feature Creation | Collect Intake Excel → L4/L3 DoR review → Assign triage lead → DCRS triage calls → Create L2 features | Incomplete DoR details, multi-week triage cycles | 1–2 weeks | 4–6 weeks |
| 2 – Prioritization | Stage 2–3 (LOB Ranking & ATL/BTL) | LOB prioritization, BigRoom planning, L1 capacity alignment | Partner dependencies, capacity constraints | 1 week | 2–3 weeks |
| 3 – Scope & Planning | Stage 4–6 | Scope validation, story breakdown, sprint planning | Ambiguous scope, late partner responses | 2 weeks | 4 weeks |
| 4 – API / Gateway Onboarding | Stage 7–9 | App ID creation, certificate generation, service account setup, APG subscription approval | Multiple approvals, manual tracker updates | 1 week | 3 weeks |
| 5 – Notifications & Kafka Setup | Stage 10–11 | Define notification types, create Kafka topics and consumer groups | KWES tool latency, cert approvals | 1–2 weeks | 3–4 weeks |
| 6 – Document Classification & Governance | Stage 12 (+ AI Docs) | Sample collection, doc classification, AI split validation | Imaging Gov review queues, exception handling | 1 week | 3 weeks |
| 7 – Partner Agreement & Volumes | Stage 13–15 | Share Partner System Agreement, collect volumes, initiate SPLI load testing | Partner data unavailability, multiple iterations | 1 week | 3 weeks |
| 8 – Metadata & Security | Stage 17–18 | Identify metadata, relationships, retention keys, apply security | Cross-LOB coordination, business unit identification | 2 weeks | 4–6 weeks |
| 9 – Retention & Profile Setup | Stage 19–22 | Fill RM Questionnaire, implement retention, define profile logic | Record coordinator approvals, config complexity | 2 weeks | 5–6 weeks |
| 10 – Testing & Validation | Stage 23–25 | Unit, Integration, UAT, SPLI sign-offs | Environment availability, late partner sign-off | 2–3 weeks | 6–8 weeks |
| 11 – Release Readiness & Change Mgmt | Stage 26 | Convert test→live profile, create CRs, APG/APA approvals, Release Transition Page | Late approvals, incomplete transition pages | 1 week | 3 weeks |
| 12 – Production Validation & Closure | Stage 27 | Tech validation, business validation, final sign-off | Delayed business testing, sign-off lags | 1 week | 3–4 weeks |

### 📈 Aggregate Impact

- Planned Overall Duration: ≈ 16–18 weeks

- Actual Average Duration: ≈ 30–36 weeks

- Primary Delay Drivers: Manual triage, partner response times, dependency approvals, non-standard data formats.

- Opportunity: Agentic automation can cut cycle time by > 50 %, centralize tracking, and predict delays through real-time AI insights.

### 💡 Prompt for Hackathon Teams

“How can we build an AI-driven Agentic Orchestrator that reduces manual hand-offs and gives real-time visibility across all stages of the Partner Onboarding Journey?”

# Onboard360 AI – Partner Onboarding Journey Simplification (Content for Hackathon Brief)

## 🧩

## Stage Group 1: Intake → Triage → Feature Creation

### Core Activities

- Partners fill and submit intake Excel form.

- L4 Product Manager reviews for Definition of Ready (DoR).

- L3 Product Manager validates triage scope and assigns triage lead.

- DCRS triage sessions (1–N calls) capture high-level design, impacted systems, and repository components.

- L2 POs create feature JIRAs once triage is closed (marked as GDAL).

### Manual Steps

- Email-based follow-ups between L4, L3, triage lead, and partner.

- Manual Excel verification for DoR.

- Manual Confluence note-taking for triage summaries.

- Manual creation of L2 and L1 JIRA features and team assignments.

### Bottlenecks / Challenges

- Repetitive data entry across Excel → JIRA → Confluence.

- Dependency on human validation for DoR.

- Triage closure delays due to unclear ownership.

- No automated traceability across parent-child JIRAs.

### Planned SLA Duration:

### 1–2 weeks

### Current Average Duration:

### 4–6 weeks (varies by LOB and triage complexity)

## 🧭

## Stage Group 2: LOB Prioritization & BigRoom Planning

### Core Activities

- LOB stakeholders rank features quarterly.

- L4/L3 POs align intake rankings with business value.

- L3 conducts BigRoom Planning to finalize “Must-Do” items.

### Manual Steps

- Spreadsheet-driven prioritization lists.

- Manual meeting scheduling and LOB follow-ups.

- Manual dependency tagging between LOB features.

### Bottlenecks / Challenges

- Static prioritization — no dynamic updates based on capacity.

- No automated effort estimation or dependency visualization.

- Cross-squad coordination delays.

### Planned SLA Duration:

### 1 week

### Current Average Duration:

### 2–3 weeks

## 🧩

## Stage Group 3: ATL/BTL Classification and Commitments

### Core Activities

- L1 teams analyze scope, estimate capacity, and mark ATL or BTL.

- Partner dependencies validated before confirming ATL commitments.

### Manual Steps

- Multiple calls across L1–L3 for commitment validation.

- Manual documentation of blockers, risks, and dependencies.

### Bottlenecks / Challenges

- Lack of centralized capacity dashboard.

- Manual revalidation every quarter.

- Partner dependencies often discovered late.

### Planned SLA Duration:

### 3–5 days

### Current Average Duration:

### 1–2 weeks

## 🧩

## Stage Group 4: Scope Identification & Partner Connect

### Core Activities

- L1 SME reviews intake and historical discussions.

- Partner connect meeting held to confirm scope, feasibility, and risks.

- Capture final scope summary and decisions.

### Manual Steps

- Email-based meeting invites and scope summaries.

- Manual note-taking and Confluence updates.

- Dependency follow-ups via Teams or email.

### Bottlenecks / Challenges

- Repetitive partner clarifications.

- No auto-summarization from JIRA or meeting transcripts.

- Risk tracking not linked to scope items.

### Planned SLA Duration:

### 1 week

### Current Average Duration:

### 2–4 weeks

## 🧩

## Stage Group 5: Development Preparation and Sprint Planning

### Core Activities

- Define stories and tasks from scope.

- Estimate timelines, dependencies, and environment readiness.

- Prepare sprint calendar aligned to release windows.

### Manual Steps

- Manually map requirements → tasks in JIRA.

- Use Excel to track test readiness, dependencies, and releases.

### Bottlenecks / Challenges

- No auto-linking of stories to release calendars.

- Repeated manual dependency mapping.

- High overhead for sprint re-baselining.

### Planned SLA Duration:

### 1 week

### Current Average Duration:

### 2–3 weeks

## 🧩

## Stage Group 6: Technical & Business Onboarding Workflows

### Core Activities

Includes multiple onboarding paths such as:

- API Gateway (APG) Onboarding

- KEES Kafka Consumer Creation

- Metadata Mapping

- Security Group Creation

- Retention Management Questionnaire (RMQ)

- Document Samples & Classification

- Partner System Agreement

### Manual Steps

- APG subscriptions, KEES requests, and Confluence trackers are handled manually.

- Excel-based metadata mapping and RMQ templates filled by hand.

- Manual sign-offs from Imaging Governance, Records Coordination, and Security Governance.

- Kafka keys and certificates raised via separate systems.

### Bottlenecks / Challenges

- Multiple disconnected workflows.

- Dependency on manual artifact reviews and approvals.

- Heavy partner communication overhead.

- High error rate in metadata and retention templates.

### Planned SLA Duration:

### 3–4 weeks

### Current Average Duration:

### 8–12 weeks

## 🧩

## Stage Group 7: Testing, Validation & Release

### Core Activities

- Unit testing by SME → Integration Testing → UAT → SPLite → Prod Validation.

- Load testing (partner and ICMP) and RM implementation validations.

### Manual Steps

- Manual testing coordination and JIRA status updates.

- Manual validation documentation for each environment.

- Change task and approval routing handled via email.

### Bottlenecks / Challenges

- Test plan and status tracking is manual.

- No single dashboard for environment progress.

- Delays in UAT sign-offs.

- Change requests often miss timelines.

### Planned SLA Duration:

### 2–3 weeks

### Current Average Duration:

### 5–7 weeks

## 🧩

## Stage Group 8: Post-Deployment & Production Validation

### Core Activities

- Profile conversion from test to live.

- Technical validations by platform support.

- Business validations by partner.

- Production sign-off and feature closure.

### Manual Steps

- Manual release transition documentation.

- Confluence page creation for each release.

- Manual follow-ups for production validation and approvals.

### Bottlenecks / Challenges

- Delayed production validations.

- No automated dependency mapping between profiles and LOBs.

- Long closure cycles even after successful deployment.

### Planned SLA Duration:

### 1 week

### Current Average Duration:

### 3–5 weeks

## ⚙️

## Overall Problem Statement for Hackathon

The Partner Onboarding lifecycle spans 27+ interdependent stages, crossing multiple squads (L1–L4) and external systems (APG, KEES, RMQ, Security, Imaging Governance, etc.).

Despite defined SLAs, average turnaround time remains 6–9 months, primarily due to manual reviews, fragmented tools, and dependency misalignment.

## 🎯

## Hackathon Goal

Design a true Agentic AI + Model Context Protocol (MCP)–powered solution that can autonomously:

- Identify, track, and manage onboarding progress across all stages

- Summarize discussions and update JIRA automatically

- Generate artifacts like metadata mapping, RMQ, and partner agreements

- Trigger contextual alerts and follow-ups

- Predict risks, delays, and dependencies dynamically

- Reduce end-to-end onboarding turnaround time from 6–9 months → 2–4 weeks (1–2 sprints)

- Enable seamless integration even when partner documents or configurations reside in external repositories (e.g., S3, ShareDrive, or staging environments)