## Sheet1
Stage Group | Core Activities | Manual Steps | Bottlenecks / Challenges | Planned SLA Duration | Current Avg. Duration
Stage Group 1: Intake → Triage → Feature Creation | Partner intake submission, DoR validation, triage scheduling, feature creation | Email follow-ups, Excel validation, manual JIRA updates | Repetitive data entry, unclear ownership, triage delays | 1–2 weeks | 4–6 weeks
Stage Group 2: LOB Prioritization & BigRoom Planning | LOB ranking, L3–L4 prioritization, BigRoom planning sessions | Manual prioritization lists, meeting scheduling | Static rankings, manual dependency mapping, coordination delays | 1 week | 2–3 weeks
Stage Group 3: ATL/BTL Commitment | L1 analysis of scope, capacity check, partner dependency validation | Manual calls and documentation for blockers and dependencies | No centralized dashboard, late partner dependency discovery | 3–5 days | 1–2 weeks
Stage Group 4: Scope Identification & Partner Connect | Review intake, collaborate with partners, finalize feasibility | Email invites, manual notes, dependency follow-ups | Repetitive clarifications, no auto-summarization | 1 week | 2–4 weeks
Stage Group 5: Development Preparation & Sprint Planning | Define stories, estimate timelines, align with release calendars | Manual JIRA mapping, Excel tracking | No auto-linking of stories to releases, re-baselining overhead | 1 week | 2–3 weeks
Stage Group 6: Technical & Business Onboarding Workflows | APG, KEES, RMQ, Metadata, Security, Doc Samples, Agreements | Manual subscriptions, Excel templates, manual approvals | Disconnected tools, manual governance, communication overload | 3–4 weeks | 8–12 weeks
Stage Group 7: Testing, Validation & Release | Unit → Integration → UAT → Load Testing → Prod Validation | Manual coordination, validation docs, change tasks via email | No unified test dashboard, UAT delays, missed CR timelines | 2–3 weeks | 5–7 weeks
Stage Group 8: Post-Deployment & Production Validation | Profile conversion, validation, partner sign-off, closure | Manual release transition docs, follow-ups, approvals | Delayed validation, manual dependency mapping | 1 week | 3–5 weeks